## Application
Phase	Sprint	Application	Group	Task	Subtask	Minimum	Medium	Maximum	Unit	Completion	Developer					Notes
0	0	Server backend	Database	Schema		0.25	0.375	0.5	man-days	0	Brad
0	0	Server backend	Database	Data		0.5	0.75	1	man-days	0	Brad
0	0	Server backend	Database	Service		0.25	0.375	0.5	man-days	0	Brad
0	0	Server backend	Account	Service		0.25	0.375	0.5	man-days	0	Brad
0	0	Server backend	Text	Service		0.25	0.375	0.5	man-days	0	Brad
0	0	Server backend	Chat	Service		0.25	0.375	0.5	man-days	0	Brad
0	0	Server backend	Message	Service		0.25	0.375	0.5	man-days	0	Brad
0	0	Server backend	Text	Endpoint		0.25	0.375	0.5	man-days	0	Brad
0	0	Server backend	Account	Endpoint		0.25	0.375	0.5	man-days	0	Brad
0	0	Server backend	Chat	Endpoint		0.25	0.375	0.5	man-days	0	Brad
0	0	Server backend	Message	Endpoint		0.25	0.375	0.5	man-days	0	Brad
0	0	Server backend	Hosting	Deployment		0.25	0.375	0.5	man-days	0	Brad
1	1	Mobile application	Account	Creation		0.5	0.75	1	man-days	0	Brad
1	1	Mobile application	Account	Connection		0.5	0.75	1	man-days	0	Brad
1	1	Mobile application	Account	Edition		0.5	0.75	1	man-days	0	Brad
1	1	Mobile application	Chat	List		0.5	0.75	1	man-days	0	Brad
1	1	Mobile application	Chat	Creation		0.5	0.75	1	man-days	0	Brad
1	1	Mobile application	Chat	Edition		0.5	0.75	1	man-days	0	Brad
1	1	Mobile application	Message	List		0.5	0.75	1	man-days	0	Brad
1	1	Mobile application	Message	Edition		0.5	0.75	1	man-days	0	Brad
1	1	Mobile application	Store	Deployment		0.25	0.375	0.5	man-days	0	Brad
2	2	Admin website	Home	Login		0.25	0.375	0.5	man-days	0	Brad
2	2	Admin website	Home	Menu		0.25	0.375	0.5	man-days	0	Brad
2	2	Admin website	Account	List		0.25	0.375	0.5	man-days	0	Brad
2	2	Admin website	Account	Edition		0.25	0.375	0.5	man-days	0	Brad
2	2	Admin website	Text	List		0.25	0.375	0.5	man-days	0	Brad
2	2	Admin website	Text	Edition		0.25	0.375	0.5	man-days	0	Brad
2	2	Admin website	Chat	List		0.25	0.375	0.5	man-days	0	Brad
2	2	Admin website	Chat	Edition		0.25	0.375	0.5	man-days	0	Brad
2	2	Admin website	Message	List		0.25	0.375	0.5	man-days	0	Brad
2	2	Admin website	Message	Edition		0.25	0.375	0.5	man-days	0	Brad
2	2	Admin website	Hosting	Deployment		0.25	0.375	0.5	man-days	0	Brad

				Total	10.25	15.375	20.5	man-days	0.55	0.82	1.10	months

Values
0	0					0	Brad
1	1					1	Jack
2	2					2	John
3	3					3	Mark
4	4					4	Mike

Sprint					Minimum	Medium	Maximum	Unit	Start Date	End Date
	0					3.25	4.875	6.5	man-days	02/12/2024	13/12/2024
	1					4.25	6.375	8.5	man-days	16/12/2024	27/12/2024
	2					2.75	4.125	5.5	man-days	30/12/2024	10/01/2025
	3					0	0	0	man-days	13/01/2025	24/01/2025
	4					0	0	0	man-days	27/01/2025	07/02/2025

Groups			Group			Minimum	Medium	Maximum	Unit	Minimum	Medium	Maximum	Unit
		Server backend	Database			1	1.5	2	man-days	0.05	0.08	0.11	months
		Server backend	Account			0.5	0.75	1	man-days	0.03	0.04	0.05	months
		Server backend	Text			0.5	0.75	1	man-days	0.03	0.04	0.05	months
		Server backend	Chat			0.5	0.75	1	man-days	0.03	0.04	0.05	months
		Server backend	Message			0.5	0.75	1	man-days	0.03	0.04	0.05	months
		Server backend	Hosting			0.25	0.375	0.5	man-days	0.01	0.02	0.03	months
		Mobile application	Account			1.5	2.25	3	man-days	0.08	0.12	0.16	months
		Mobile application	Chat			1.5	2.25	3	man-days	0.08	0.12	0.16	months
		Mobile application	Message			1	1.5	2	man-days	0.05	0.08	0.11	months
		Mobile application	Store			0.25	0.375	0.5	man-days	0.01	0.02	0.03	months
		Admin website	Home			0.5	0.75	1	man-days	0.03	0.04	0.05	months
		Admin website	Account			0.5	0.75	1	man-days	0.03	0.04	0.05	months
		Admin website	Text			0.5	0.75	1	man-days	0.03	0.04	0.05	months
		Admin website	Chat			0.5	0.75	1	man-days	0.03	0.04	0.05	months
		Admin website	Message			0.5	0.75	1	man-days	0.03	0.04	0.05	months
		Admin website	Hosting			0.25	0.375	0.5	man-days	0.01	0.02	0.03	months

				Total	10.25	15.375	20.5	man-days	0.55	0.82	1.10	months

Phases					Minimum	Medium	Maximum	Unit	Minimum	Medium	Maximum	Unit	Sum	Min. Date	Max. Date	Description
0					3.25	4.875	6.5	man-days	0.17	0.26	0.35	months	0.35	21/12/2024	04/01/2025	Server backend
1					4.25	6.375	8.5	man-days	0.23	0.34	0.46	months	0.80	04/01/2025	18/01/2025	Mobile application
2					2.75	4.125	5.5	man-days	0.15	0.22	0.29	months	1.10	13/01/2025	27/01/2025	Admin website
3					0	0	0	man-days	0.00	0.00	0.00	months	1.10	13/01/2025	27/01/2025
4					0	0	0	man-days	0.00	0.00	0.00	months	1.10	13/01/2025	27/01/2025

				Total	10.25	15.375	20.5	man-days	0.55	0.82	1.10	months

## Configuration
Name	Value
Team velocity	1
Medium factor	1.5
Maximum factor	2
Days per month	18.66