## Application
Phase	Sprint	Application	Group	Task	Minimum	Medium	Maximum	Unit	Urgency	Developers	Design Completion	Design Status	Code Completion	Code Status		Notes	Issues
1	1	Mobile	Account	Account creation	1	1.5	2	man-days	0	Brad, Jack	100%	validated	0%	upcoming
1	1	Mobile	Account	Account edition	1	1.5	2	man-days	0	Brad, Jack	100%	validated	0%	upcoming
1	1	Mobile	Account	Account connection	1	1.5	2	man-days	0	Brad, Jack	100%	validated	0%	upcoming
1	2	Mobile	Chat	Chat list	1	1.5	2	man-days	0	Brad, Jack	100%	validated	0%	missing
1	2	Mobile	Chat	Chat creation	1	1.5	2	man-days	0	Brad, Jack	100%	validated	0%	missing
1	2	Mobile	Chat	Chat edition	1	1.5	2	man-days	0	Brad, Jack	100%	validated	0%	missing
1	2	Mobile	Chat	Message list	1	1.5	2	man-days	0	Brad, Jack	100%	validated	0%	missing
1	2	Mobile	Chat	Message edition	1	1.5	2	man-days	0	Brad, Jack	100%	validated	0%	missing
0	0	Server	Database	Service	0.5	0.75	1	man-days	0	Brad, Jack	100%	validated	100%	in progress
0	0	Server	Text	Service	0.5	0.75	1	man-days	0	Brad, Jack	100%	validated	50%	in progress
0	0	Server	Account	Service	0.5	0.75	1	man-days	0	Brad, Jack	100%	validated	50%	in progress
0	0	Server	Chat	Service	0.5	0.75	1	man-days	0	Brad, Jack	100%	validated	0%	in progress
0	0	Server	Message	Service	0.5	0.75	1	man-days	0	Brad, Jack	100%	validated	0%	in progress
0	0	Server	Text	Endpoint	0.5	0.75	1	man-days	0	Brad, Jack	100%	validated	0%	in progress
0	0	Server	Account	Endpoint	0.5	0.75	1	man-days	0	Brad, Jack	100%	validated	0%	in progress
0	0	Server	Chat	Endpoint	0.5	0.75	1	man-days	0	Brad, Jack	100%	validated	0%	in progress
0	0	Server	Message	Endpoint	0.5	0.75	1	man-days	0	Brad, Jack	100%	validated	0%	in progress
2	3	Admin	Dashboard	Connection	1	1.5	2	man-days	0	Brad, Jack	100%	validated	0%	missing
2	3	Admin	Dashboard	Entity list	1	1.5	2	man-days	0	Brad, Jack	100%	validated	0%	missing
2	3	Admin	Entity	Text list	1	1.5	2	man-days	0	Brad, Jack	100%	validated	0%	missing
2	3	Admin	Entity	Text edition	1	1.5	2	man-days	0	Brad, Jack	100%	validated	0%	missing
2	4	Admin	Entity	Account list	0.5	0.75	1	man-days	0	Brad, Jack	0%	upcoming	0%	missing
2	4	Admin	Entity	Account edition	0.5	0.75	1	man-days	0	Brad, Jack	0%	upcoming	0%	missing
2	4	Admin	Entity	Chat list	0.5	0.75	1	man-days	0	Brad, Jack	0%	upcoming	0%	missing
2	4	Admin	Entity	Chat edition	0.5	0.75	1	man-days	0	Brad, Jack	0%	upcoming	0%	missing
2	4	Admin	Entity	Message list	0.5	0.75	1	man-days	0	Brad, Jack	0%	upcoming	0%	missing
2	4	Admin	Entity	Message edition	0.5	0.75	1	man-days	0	Brad, Jack	0%	upcoming	0%	missing

				Total	19.5	29.25	39	man-days	0.70	1.05	1.39	months

Values
0	0								0	Brad		missing		missing
1	1								1	Jack		upcoming		upcoming
2	2								2	John		in progress		in progress
3	3								3	Mark		evaluated		tested
4	4								4	Mike		validated		deployed

Sprint					Minimum	Medium	Maximum	Unit	Start Date	End Date
0					4.5	6.75	9	man-days	25/11/2024	01/12/2024
1					3	4.5	6	man-days	02/12/2024	08/12/2024
2					5	7.5	10	man-days	09/12/2024	15/12/2024
3					4	6	8	man-days	16/12/2024	22/12/2024
4					3	4.5	6	man-days	23/12/2024	29/12/2024

Groups			Group		Minimum	Medium	Maximum	Unit	Minimum	Medium	Maximum	Unit
			Account		4	6	8	man-days	0.14	0.21	0.29	months
			Chat		6	9	12	man-days	0.21	0.32	0.43	months
			Dashboard		2	3	4	man-days	0.07	0.11	0.14	months
			Database		0.5	0.75	1	man-days	0.02	0.03	0.04	months
			Entity		5	7.5	10	man-days	0.18	0.27	0.36	months
			Message		1	1.5	2	man-days	0.04	0.05	0.07	months
			Text		1	1.5	2	man-days	0.04	0.05	0.07	months

				Total	19.5	29.25	39	man-days	0.70	1.05	1.39	months

Phases					Minimum	Medium	Maximum	Unit	Minimum	Medium	Maximum	Unit	Sum	Min. Date	Max. Date	Description
0					4.5	6.75	9	man-days	0.16	0.24	0.32	months	0.32	17/12/2024	31/12/2024	Server backend
1					8	12	16	man-days	0.29	0.43	0.57	months	0.89	04/01/2025	18/01/2025	Mobile frontend
2					7	10.5	14	man-days	0.25	0.38	0.50	months	1.39	19/01/2025	02/02/2025	Admin frontend
3					0	0	0	man-days	0.00	0.00	0.00	months	1.39	19/01/2025	02/02/2025
4					0	0	0	man-days	0.00	0.00	0.00	months	1.39	19/01/2025	02/02/2025

				Total	19.5	29.25	39	man-days	0.70	1.05	1.39	months

## Configuration
Name	Value
Team velocity	1.5
Medium factor	1.5
Maximum factor	2