## Application
Phase	Sprint	Application	Group	Task	Subtask	Minimum Man-days	Medium Man-days	Maximum Man-days	Due Date	Priority	Developer	Velocity	Minimum Man-days	Medium Man-days	Maximum Man-days	Status	Notes
0	0	Server backend	Database	Schema		0.5	0.8	1		4	Brad	1	0.5	0.8	1	0
0	0	Server backend	Database	Data		0.5	0.8	1		4	Brad	1	0.5	0.8	1	0
0	0	Server backend	Database	Service		0.5	0.8	1		4	Brad	1	0.5	0.8	1	0
0	0	Server backend	Account	Service		0.5	0.8	1		2	Jack	0.9	0.6	0.8	1.1	0
0	0	Server backend	Text	Service		0.5	0.8	1		2	Jack	0.9	0.6	0.8	1.1	0
0	0	Server backend	Chat	Service		0.5	0.8	1		2	Jack	0.9	0.6	0.8	1.1	0
0	0	Server backend	Message	Service		0.5	0.8	1		2	Jack	0.9	0.6	0.8	1.1	0
0	0	Server backend	Text	Endpoint		0.5	0.8	1		2	John	0.8	0.6	0.9	1.3	0
0	0	Server backend	Account	Endpoint		0.5	0.8	1		2	John	0.8	0.6	0.9	1.3	0
0	0	Server backend	Chat	Endpoint		0.5	0.8	1		2	John	0.8	0.6	0.9	1.3	0
0	0	Server backend	Message	Endpoint		0.5	0.8	1		2	John	0.8	0.6	0.9	1.3	0
1	0	Mobile application	Account	Creation		1	1.5	2		0	Brad	1	1	1.5	2	0
1	0	Mobile application	Account	Connection		1	1.5	2		0	Brad	1	1	1.5	2	0
1	1	Mobile application	Account	Edition		1	1.5	2		0	Brad	1	1	1.5	2	0
1	0	Mobile application	Chat	List		0.5	0.8	1		0	Jack	0.9	0.6	0.8	1.1	0
1	0	Mobile application	Chat	Creation		1	1.5	2		0	Jack	0.9	1.1	1.7	2.2	0
1	1	Mobile application	Chat	Edition		1	1.5	2		0	Jack	0.9	1.1	1.7	2.2	0
1	0	Mobile application	Message	List		1	1.5	2		0	John	0.8	1.3	1.9	2.5	0
1	1	Mobile application	Message	Edition		1	1.5	2		0	John	0.8	1.3	1.9	2.5	0
2	1	Admin website	Home	Login		0.5	0.8	1		0	Brad	1	0.5	0.8	1	0
2	1	Admin website	Home	Menu		0.5	0.8	1		0	Brad	1	0.5	0.8	1	0
2	1	Admin website	Account	List		0.5	0.8	1		0	Brad	1	0.5	0.8	1	0
2	1	Admin website	Account	Edition		0.5	0.8	1		0	Brad	1	0.5	0.8	1	0
2	1	Admin website	Text	List		0.5	0.8	1		0	Jack	0.9	0.6	0.8	1.1	0
2	1	Admin website	Text	Edition		0.5	0.8	1		0	Jack	0.9	0.6	0.8	1.1	0
2	1	Admin website	Chat	List		0.5	0.8	1		0	Jack	0.9	0.6	0.8	1.1	0
2	1	Admin website	Chat	Edition		0.5	0.8	1		0	Jack	0.9	0.6	0.8	1.1	0
2	1	Admin website	Message	List		0.5	0.8	1		0	John	0.8	0.6	0.9	1.3	0
2	1	Admin website	Message	Edition		0.5	0.8	1		0	John	0.8	0.6	0.9	1.3	0

					Total	18	27	36					20	30	39.9

Phase	Sprint									Priority	Developer	Velocity				Status
0	0									0	Brad	1				0	to do
1	1									1	Jack	0.9				1	to design
2	2									2	John	0.8				2	to develop
3	3									3	Mark	0.7				3	in progress
4	4									4	Mike	0.6				4	to test
																5	to deploy
																6	done

	Sprint					Start Date	End Date	Team Availability	Team / Man-days	Brad / Man-days	Jack / Man-days	John / Man-days	Mark / Man-days	Mike / Man-days
	0					09/12/2024	20/12/2024	24	22.3	7	7.8	7.5	0	0
	1					23/12/2024	03/01/2025	24	17.7	6	6.7	5	0	0
	2					06/01/2025	17/01/2025	24	0	0	0	0	0	0
	3					20/01/2025	31/01/2025	24	0	0	0	0	0	0
	4					03/02/2025	14/02/2025	24	0	0	0	0	0	0

		Application	Group			Minimum Man-days	Medium Man-days	Maximum Man-days
		Server backend	Database			1.5	2.3	3
		Server backend	Account			1.2	1.8	2.4
		Server backend	Text			1.2	1.8	2.4
		Server backend	Chat			1.2	1.8	2.4
		Server backend	Message			1.2	1.8	2.4
		Server backend	Operation			0	0	0
		Mobile application	Account			3	4.5	6
		Mobile application	Chat			2.8	4.2	5.6
		Mobile application	Message			2.5	3.8	5
		Mobile application	Operation			0	0	0
		Admin website	Home			1	1.5	2
		Admin website	Account			1	1.5	2
		Admin website	Text			1.1	1.7	2.2
		Admin website	Chat			1.1	1.7	2.2
		Admin website	Message			1.3	1.9	2.5
		Admin website	Operation			0	0	0

					Total	20	30	39.9

Phases						Minimum Man-days	Medium Man-days	Maximum Man-days	Minimum Man-months	Medium Man-months	Maximum Man-months	Team Availability	Total / Months	Min. Date	Max. Date	Due Date	Description
0						6.2	9.3	12.4	0.3	0.5	0.7	2.4	0.3	18/12/2024	29/12/2024		Server backend
1						8.3	12.4	16.6	0.4	0.7	0.9	2.4	0.6	29/12/2024	09/01/2025		Mobile application
2						5.5	8.2	10.9	0.3	0.4	0.6	2.4	0.9	06/01/2025	17/01/2025		Admin website
3						0	0	0	0	0	0	2.4	0.9	06/01/2025	17/01/2025
4						0	0	0	0	0	0	2.4	0.9	06/01/2025	17/01/2025

					Total	20	30	39.9	1.1	1.6	2.1		0.9	06/01/2025	17/01/2025

## Configuration
Name	Value
Current sprint date	09/12/2024
Working days per month	18.66
Medium uncertainty factor	1.5
Maximum uncertainty factor	2