## Application
Phase	Sprint	Application	Group	Task	Subtask	Minimum Man-days	Medium Man-days	Maximum Man-days	Priority	Developer	Velocity	Minimum Man-days	Medium Man-days	Maximum Man-days	Status	Due Date	Notes
0	0	Server backend	Database	Schema		1	1.5	2	4	Brad	1	1	1.5	2	0
0	0	Server backend	Database	Data		1	1.5	2	4	Brad	1	1	1.5	2	0
0	0	Server backend	Database	Service		1	1.5	2	4	Brad	1	1	1.5	2	0
0	0	Server backend	Account	Service		1	1.5	2	2	Jack	0.9	1.1	1.7	2.2	0
0	0	Server backend	Text	Service		1	1.5	2	2	Jack	0.9	1.1	1.7	2.2	0
0	0	Server backend	Chat	Service		1	1.5	2	2	Jack	0.9	1.1	1.7	2.2	0
0	0	Server backend	Message	Service		1	1.5	2	2	Jack	0.9	1.1	1.7	2.2	0
0	0	Server backend	Text	Endpoint		1	1.5	2	2	John	0.8	1.3	1.9	2.5	0
0	0	Server backend	Account	Endpoint		1	1.5	2	2	John	0.8	1.3	1.9	2.5	0
0	0	Server backend	Chat	Endpoint		1	1.5	2	2	John	0.8	1.3	1.9	2.5	0
0	0	Server backend	Message	Endpoint		1	1.5	2	2	John	0.8	1.3	1.9	2.5	0
0	0	Server backend	Operation	Deployment		1	1.5	2	2	Brad	1	1	1.5	2	0
1	1	Mobile application	Account	Creation		1	1.5	2	0	Brad	1	1	1.5	2	0
1	1	Mobile application	Account	Connection		1	1.5	2	0	Brad	1	1	1.5	2	0
1	1	Mobile application	Account	Edition		1	1.5	2	0	Brad	1	1	1.5	2	0
1	1	Mobile application	Chat	List		1	1.5	2	0	Jack	0.9	1.1	1.7	2.2	0
1	1	Mobile application	Chat	Creation		1	1.5	2	0	Jack	0.9	1.1	1.7	2.2	0
1	1	Mobile application	Chat	Edition		1	1.5	2	0	Jack	0.9	1.1	1.7	2.2	0
1	1	Mobile application	Message	List		1	1.5	2	0	John	0.8	1.3	1.9	2.5	0
1	1	Mobile application	Message	Edition		1	1.5	2	0	John	0.8	1.3	1.9	2.5	0
1	1	Mobile application	Operation	Deployment		1	1.5	2	0	John	0.8	1.3	1.9	2.5	0
2	2	Admin website	Home	Login		1	1.5	2	0	Brad	1	1	1.5	2	0
2	2	Admin website	Home	Menu		1	1.5	2	0	Brad	1	1	1.5	2	0
2	2	Admin website	Account	List		1	1.5	2	0	Brad	1	1	1.5	2	0
2	2	Admin website	Account	Edition		1	1.5	2	0	Brad	1	1	1.5	2	0
2	2	Admin website	Text	List		1	1.5	2	0	Jack	0.9	1.1	1.7	2.2	0
2	2	Admin website	Text	Edition		1	1.5	2	0	Jack	0.9	1.1	1.7	2.2	0
2	2	Admin website	Chat	List		1	1.5	2	0	Jack	0.9	1.1	1.7	2.2	0
2	2	Admin website	Chat	Edition		1	1.5	2	0	Jack	0.9	1.1	1.7	2.2	0
2	2	Admin website	Message	List		1	1.5	2	0	John	0.8	1.3	1.9	2.5	0
2	2	Admin website	Message	Edition		1	1.5	2	0	John	0.8	1.3	1.9	2.5	0
2	2	Admin website	Operation	Deployment		1	1.5	2	0	John	0.8	1.3	1.9	2.5	0

					Total	32	48	64				35.7	53.6	71.4

Phase	Sprint								Priority	Developer	Velocity				Status
0	0								0	Brad	1				0	missing
1	1								1	Jack	0.9				1	designed
2	2								2	John	0.8				2	in progress
3	3								3	Mark	0.7				3	done
4	4								4	Mike	0.6				4	validated
															5	deployed

	Sprint					Start Date	End Date	Team Capacity	Team / Man-days	Brad / Man-days	Jack / Man-days	John / Man-days	Mark / Man-days	Mike / Man-days
	0					02/12/2024	13/12/2024	30	26.9	8	8.9	10	0	0
	1					16/12/2024	27/12/2024	30	20.2	6	6.7	7.5	0	0
	2					30/12/2024	10/01/2025	30	24.4	8	8.9	7.5	0	0
	3					13/01/2025	24/01/2025	30	0	0	0	0	0	0
	4					27/01/2025	07/02/2025	30	0	0	0	0	0	0

		Application	Group			Minimum Man-days	Medium Man-days	Maximum Man-days
		Server backend	Database			3	4.5	6
		Server backend	Account			2.4	3.5	4.7
		Server backend	Text			2.4	3.5	4.7
		Server backend	Chat			2.4	3.5	4.7
		Server backend	Message			2.4	3.5	4.7
		Server backend	Operation			1	1.5	2
		Mobile application	Account			3	4.5	6
		Mobile application	Chat			3.3	5	6.7
		Mobile application	Message			2.5	3.8	5
		Mobile application	Operation			1.3	1.9	2.5
		Admin website	Home			2	3	4
		Admin website	Account			2	3	4
		Admin website	Text			2.2	3.3	4.4
		Admin website	Chat			2.2	3.3	4.4
		Admin website	Message			2.5	3.8	5
		Admin website	Operation			1.3	1.9	2.5

					Total	35.7	53.6	71.4

Phases						Minimum Man-days	Medium Man-days	Maximum Man-days	Minimum Man-months	Medium Man-months	Maximum Man-months	Team Capacity	Total / Months	Min. Date	Max. Date		Description
0						13.4	20.2	26.9	0.7	1.1	1.4	3	0.5	17/12/2024	28/12/2024		Server backend
1						10.1	15.1	20.2	0.5	0.8	1.1	3	0.8	28/12/2024	08/01/2025		Mobile application
2						12.2	18.3	24.4	0.7	1	1.3	3	1.3	10/01/2025	21/01/2025		Admin website
3						0	0	0	0	0	0	3	1.3	10/01/2025	21/01/2025
4						0	0	0	0	0	0	3	1.3	10/01/2025	21/01/2025

					Total	35.7	53.6	71.4	1.9	2.9	3.8		1.3

## Configuration
Name	Value
Current sprint date	02/12/2024
Working days per month	18.66
Medium uncertainty factor	1.5
Maximum uncertainty factor	2