## Application
Phase	Sprint	Application	Group	Task	Subtask	Minimum	Medium	Maximum	Unit	Completion	Developer					Notes
0	0	Server backend	Database	Schema		0.5	0.75	1	man-days	0	Brad
0	0	Server backend	Database	Data		0.5	0.75	1	man-days	0	Brad
0	0	Server backend	Database	Service		0.5	0.75	1	man-days	0	Brad
0	0	Server backend	Account	Service		0.5	0.75	1	man-days	0	Brad
0	0	Server backend	Text	Service		0.5	0.75	1	man-days	0	Brad
0	0	Server backend	Chat	Service		0.5	0.75	1	man-days	0	Brad
0	0	Server backend	Message	Service		0.5	0.75	1	man-days	0	Brad
0	0	Server backend	Text	Endpoint		0.25	0.375	0.5	man-days	0	Brad
0	0	Server backend	Account	Endpoint		0.25	0.375	0.5	man-days	0	Brad
0	0	Server backend	Chat	Endpoint		0.25	0.375	0.5	man-days	0	Brad
0	0	Server backend	Message	Endpoint		0.25	0.375	0.5	man-days	0	Brad
0	0	Server backend	Instance	Deployment		0.25	0.375	0.5	man-days	0	Brad
0	0	Server backend	Instance	Tests		0.5	0.75	1	man-days	0	Brad
1	1	Mobile application	Account	Creation		1	1.5	2	man-days	0	Brad
1	1	Mobile application	Account	Connection		1	1.5	2	man-days	0	Brad
1	1	Mobile application	Account	Edition		1	1.5	2	man-days	0	Brad
1	2	Mobile application	Chat	List		1	1.5	2	man-days	0	Brad
1	2	Mobile application	Chat	Creation		1	1.5	2	man-days	0	Brad
1	2	Mobile application	Chat	Edition		1	1.5	2	man-days	0	Brad
1	2	Mobile application	Message	List		1	1.5	2	man-days	0	Brad
1	2	Mobile application	Message	Edition		1	1.5	2	man-days	0	Brad
2	3	Admin website	Home	Login		0.5	0.75	1	man-days	0	Brad
2	3	Admin website	Home	Menu		0.5	0.75	1	man-days	0	Brad
2	3	Admin website	Account	List		0.5	0.75	1	man-days	0	Brad
2	3	Admin website	Account	Edition		0.5	0.75	1	man-days	0	Brad
2	3	Admin website	Text	List		0.5	0.75	1	man-days	0	Brad
2	3	Admin website	Text	Edition		0.5	0.75	1	man-days	0	Brad
2	3	Admin website	Chat	List		0.5	0.75	1	man-days	0	Brad
2	3	Admin website	Chat	Edition		0.5	0.75	1	man-days	0	Brad
2	3	Admin website	Message	List		0.5	0.75	1	man-days	0	Brad
2	3	Admin website	Message	Edition		0.5	0.75	1	man-days	0	Brad

				Total	18.25	27.375	36.5	man-days	0.98	1.47	1.96	months

Values
0	0	Server backend					0	Brad
1	1	Mobile application					1	Jack
2	2	Admin website					2	John
3	3					3	Mark
4	4					4	Mike

Sprint					Minimum	Medium	Maximum	Unit	Start Date	End Date
	0					5.25	7.875	10.5	man-days	02/12/2024	13/12/2024
	1					3	4.5	6	man-days	16/12/2024	27/12/2024
	2					5	7.5	10	man-days	30/12/2024	10/01/2025
	3					5	7.5	10	man-days	13/01/2025	24/01/2025
	4					0	0	0	man-days	27/01/2025	07/02/2025

Groups			Group			Minimum	Medium	Maximum	Unit	Minimum	Medium	Maximum	Unit
		Server backend	Database			1.5	2.25	3	man-days	0.08	0.12	0.16	months
		Server backend	Account			0.75	1.125	1.5	man-days	0.04	0.06	0.08	months
		Server backend	Text			0.75	1.125	1.5	man-days	0.04	0.06	0.08	months
		Server backend	Chat			0.75	1.125	1.5	man-days	0.04	0.06	0.08	months
		Server backend	Message			0.75	1.125	1.5	man-days	0.04	0.06	0.08	months
		Server backend	Instance			0.75	1.125	1.5	man-days	0.04	0.06	0.08	months
		Mobile application	Account			3	4.5	6	man-days	0.16	0.24	0.32	months
		Mobile application	Chat			3	4.5	6	man-days	0.16	0.24	0.32	months
		Mobile application	Message			2	3	4	man-days	0.11	0.16	0.21	months
		Admin website	Home			1	1.5	2	man-days	0.05	0.08	0.11	months
		Admin website	Account			1	1.5	2	man-days	0.05	0.08	0.11	months
		Admin website	Text			1	1.5	2	man-days	0.05	0.08	0.11	months
		Admin website	Chat			1	1.5	2	man-days	0.05	0.08	0.11	months
		Admin website	Message			1	1.5	2	man-days	0.05	0.08	0.11	months

				Total	18.25	27.375	36.5	man-days	0.98	1.47	1.96	months

Phases					Minimum	Medium	Maximum	Unit	Minimum	Medium	Maximum	Unit	Sum	Min. Date	Max. Date	Description
0					5.25	7.875	10.5	man-days	0.28	0.42	0.56	months	0.56	28/12/2024	11/01/2025	Server backend
1					8	12	16	man-days	0.43	0.64	0.86	months	1.42	23/01/2025	06/02/2025	Mobile application
2					5	7.5	10	man-days	0.27	0.40	0.54	months	1.96	08/02/2025	22/02/2025	Admin website
3					0	0	0	man-days	0.00	0.00	0.00	months	1.96	08/02/2025	22/02/2025
4					0	0	0	man-days	0.00	0.00	0.00	months	1.96	08/02/2025	22/02/2025

				Total	18.25	27.375	36.5	man-days	0.98	1.47	1.96	months

## Configuration
Name	Value
Team velocity	1
Medium factor	1.5
Maximum factor	2
Days per month	18.66