## Application
Phase	Sprint	Application	Group	Task	Minimum	Medium	Maximum	Unit	Urgency	Developers	Design Status	Code Status				Notes	Issues
0	0	Server backend	Database	Schema	0.5	0.75	1	man-days	0	Brad	validated	in progress
0	0	Server backend	Database	Data	0.5	0.75	1	man-days	0	Brad	validated	in progress
0	0	Server backend	Database	Service	0.5	0.75	1	man-days	0	Brad	validated	in progress
0	0	Server backend	Account	Service	0.5	0.75	1	man-days	0	Brad	validated	in progress
0	0	Server backend	Text	Service	0.5	0.75	1	man-days	0	Brad	validated	in progress
0	0	Server backend	Chat	Service	0.5	0.75	1	man-days	0	Brad	validated	in progress
0	0	Server backend	Message	Service	0.5	0.75	1	man-days	0	Brad	validated	in progress
0	0	Server backend	Text	Endpoint	0.25	0.375	0.5	man-days	0	Brad	validated	in progress
0	0	Server backend	Account	Endpoint	0.25	0.375	0.5	man-days	0	Brad	validated	in progress
0	0	Server backend	Chat	Endpoint	0.25	0.375	0.5	man-days	0	Brad	validated	in progress
0	0	Server backend	Message	Endpoint	0.25	0.375	0.5	man-days	0	Brad	validated	in progress
0	0	Server backend	Instance	Deployment	0.25	0.375	0.5	man-days	0	Brad	validated	in progress
0	0	Server backend	Instance	Tests	0.5	0.75	1	man-days	0	Brad	validated	in progress
1	1	Mobile application	Account	Creation	1	1.5	2	man-days	0	Brad	validated	upcoming
1	1	Mobile application	Account	Connection	1	1.5	2	man-days	0	Brad	validated	upcoming
1	1	Mobile application	Account	Edition	1	1.5	2	man-days	0	Brad	validated	upcoming
1	2	Mobile application	Chat	List	1	1.5	2	man-days	0	Brad	validated	missing
1	2	Mobile application	Chat	Creation	1	1.5	2	man-days	0	Brad	validated	missing
1	2	Mobile application	Chat	Edition	1	1.5	2	man-days	0	Brad	validated	missing
1	2	Mobile application	Message	List	1	1.5	2	man-days	0	Brad	validated	missing
1	2	Mobile application	Message	Edition	1	1.5	2	man-days	0	Brad	validated	missing
2	3	Admin website	Home	Login	0.5	0.75	1	man-days	0	Brad	validated	missing
2	3	Admin website	Home	Menu	0.5	0.75	1	man-days	0	Brad	validated	missing
2	3	Admin website	Account	List	0.5	0.75	1	man-days	0	Brad	validated	missing
2	3	Admin website	Account	Edition	0.5	0.75	1	man-days	0	Brad	validated	missing
2	3	Admin website	Text	List	0.5	0.75	1	man-days	0	Brad	upcoming	missing
2	3	Admin website	Text	Edition	0.5	0.75	1	man-days	0	Brad	upcoming	missing
2	3	Admin website	Chat	List	0.5	0.75	1	man-days	0	Brad	upcoming	missing
2	3	Admin website	Chat	Edition	0.5	0.75	1	man-days	0	Brad	upcoming	missing
2	3	Admin website	Message	List	0.5	0.75	1	man-days	0	Brad	upcoming	missing
2	3	Admin website	Message	Edition	0.5	0.75	1	man-days	0	Brad	upcoming	missing

				Total	18.25	27.375	36.5	man-days	0.98	1.47	1.96	months

Values
0	0	Server backend							0	Brad	missing	missing
1	1	Mobile application							1	Jack	upcoming	upcoming
2	2	Admin website							2	John	in progress	in progress
3	3								3	Mark	evaluated	tested
4	4								4	Mike	validated	deployed

Sprint					Minimum	Medium	Maximum	Unit	Start Date	End Date
	0				5.25	7.875	10.5	man-days	02/12/2024	13/12/2024
	1				3	4.5	6	man-days	16/12/2024	27/12/2024
	2				5	7.5	10	man-days	30/12/2024	10/01/2025
	3				5	7.5	10	man-days	13/01/2025	24/01/2025
	4				0	0	0	man-days	27/01/2025	07/02/2025

Groups			Group		Minimum	Medium	Maximum	Unit	Minimum	Medium	Maximum	Unit
		Server backend	Database		1.5	2.25	3	man-days	0.08	0.12	0.16	months
		Server backend	Account		0.75	1.125	1.5	man-days	0.04	0.06	0.08	months
		Server backend	Text		0.75	1.125	1.5	man-days	0.04	0.06	0.08	months
		Server backend	Chat		0.75	1.125	1.5	man-days	0.04	0.06	0.08	months
		Server backend	Message		0.75	1.125	1.5	man-days	0.04	0.06	0.08	months
		Server backend	Instance		0.75	1.125	1.5	man-days	0.04	0.06	0.08	months
		Mobile application	Account		3	4.5	6	man-days	0.16	0.24	0.32	months
		Mobile application	Chat		3	4.5	6	man-days	0.16	0.24	0.32	months
		Mobile application	Message		2	3	4	man-days	0.11	0.16	0.21	months
		Admin website	Home		1	1.5	2	man-days	0.05	0.08	0.11	months
		Admin website	Account		1	1.5	2	man-days	0.05	0.08	0.11	months
		Admin website	Text		1	1.5	2	man-days	0.05	0.08	0.11	months
		Admin website	Chat		1	1.5	2	man-days	0.05	0.08	0.11	months
		Admin website	Message		1	1.5	2	man-days	0.05	0.08	0.11	months

				Total	18.25	27.375	36.5	man-days	0.98	1.47	1.96	months

Phases					Minimum	Medium	Maximum	Unit	Minimum	Medium	Maximum	Unit	Sum	Min. Date	Max. Date	Description
0					5.25	7.875	10.5	man-days	0.28	0.42	0.56	months	0.56	27/12/2024	10/01/2025	Server backend
1					8	12	16	man-days	0.43	0.64	0.86	months	1.42	22/01/2025	05/02/2025	Mobile application
2					5	7.5	10	man-days	0.27	0.40	0.54	months	1.96	07/02/2025	21/02/2025	Admin website
3					0	0	0	man-days	0.00	0.00	0.00	months	1.96	07/02/2025	21/02/2025
4					0	0	0	man-days	0.00	0.00	0.00	months	1.96	07/02/2025	21/02/2025

				Total	18.25	27.375	36.5	man-days	0.98	1.47	1.96	months

## Configuration
Name	Value
Team velocity	1
Medium factor	1.5
Maximum factor	2
Days per month	18.66